## Klonepalm Basic
Klonepalm Example - basic format
Schedule
| Activity | Node | Predecessors | duration | ES | EF | LS | LF | Slack | Critical?
| Prototype Design | A |  | 90 | 0 | 90 | 0 | 90 | 0 | 1
| Purchase Materials | B | A | 15 | 90 | 105 | 95 | 110 | 5
| Manufacture Prototypes | C | B | 5 | 105 | 110 | 110 | 115 | 5
| Revise Design | D | G | 20 | 129 | 149 | 129 | 149 | 0 | 1
| Initial production | E | D | 21 | 149 | 170 | 173 | 194 | 24
| Staff Training | F | A | 25 | 90 | 115 | 90 | 115 | 0 | 1
| Staff Input on Prototype | G | C,F | 14 | 115 | 129 | 115 | 129 | 0 | 1
| Sales Training | H | D | 28 | 149 | 177 | 166 | 194 | 17
| Proproduction Advertising | I | A | 30 | 90 | 120 | 119 | 149 | 29
| Post-redesign Advertising | J | D, I | 45 | 149 | 194 | 149 | 194 | 0 | 1
| Finish | Fin | E, H, J | 0 | 194 | 194 | 194 | 194 | 0 | 1
| Time = | 194