Managing costs  with PERT

(Basic ideas of PERT/Cost)

PERT/CPM is used for management of projects once they are underway – particularly  monitoring the progress of the project, in keeping track of costs and other resources, and in scheduling.

We will look at the use in cost oversight, using the following project

|  |  |  |  |  |  |  |  |  | Total | Weekly |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity | Pred | Time | ES | EF | LS | LF | Slack | Crit | Cost | Cost |
| A |  | 3 | 0 | 3 | 3 | 6 | 3 |  | 6000 | 2000 |
| B | A | 2 | 3 | 5 | 6 | 8 | 3 |  | 4000 | 2000 |
| C |  | 8 | 0 | 8 | 0 | 8 | 0 | Y | 16000 | 2000 |
| D | B.C | 6 | 8 | 14 | 8 | 14 | 0 | Y | 18000 | 3000 |
| E | C | 4 | 8 | 12 | 10 | 14 | 2 |  | 20000 | 5000 |
| F | D,E | 5 | 14 | 19 | 14 | 19 | 0 | Y | 15000 | 3000 |
| G | D,E | 1 | 14 | 15 | 18 | 19 | 4 |  | 2000 | 2000 |
| H | F | 5 | 19 | 24 | 20 | 25 | 1 |  | 5000 | 1000 |
| I | F,G | 6 | 19 | 25 | 19 | 25 | 0 | Y | 12000 | 2000 |
| Finish |  |  | 25 | 25 | 25 | 25 |  |  |  |  |

The standard assumption for PERT/Cost is that the cost of an activity accrues at a steady rate - the same amount each week..

With this assumption, we get the Early-start budget chart shown in the workbook --- It looks a great deal like the Gantt chart based on earliest times, but indicates per week costs - at the bottom, we have total costs for the week and cumulative (total) costs for the project through the week.

We also get the Latest-times budget shown.

Notice that each activity is shown starting/finishing at the end of the week indicated in the ES,EF columns – so Activity E starts at the end of week 8 (beginning of week 9) for earliest times and the end of week 10 (beginning of week 11) for latest times.

This allows planning of expenditures, having money on hand, etc.  It also allows for some flexibility in planning – since activities can start between earliest and latest times, they can be delayed to improve cash-flow problems, or planned to avoid critical periods.

We can graph the earliest and latest time cost schedules together – the dots indicate where activities begin/end (and rate of spending changes). The area between the graphs indicates the area of flexibility in planning (by delaying the start of activities).

The budget provides a tool for managing the project- for comparing expenditures to the budget. Usually knowing the total amount spent is not enough –delays in starting activities may hold down expenditures (because the activities haven’t started) when the project is in trouble.

At various times (possibly weekly – more likely at intervals)  the manager  obtains a summary of activities completed, activities under way, what percentage of each activity is completed, how projected cost compares to actual cost.

For our project, we might have the following at the end of the fifth week:
Activity	Budgeted cost	%complete	value completed	actual cost (to date)	cost overrun

A	6000	100	6000	5500	-500

B	4000	50	2000	2500	500

C	16000	75	12000	13000	1000

Total				20000	21000

Other activities – which have not yet started – do not appear.

This would tell the manager that B is behind the schedule – but this is not yet a problem because the slack is not all used up  C is a bit ahead of schedule. The cost overruns on B  and  C are a bit large – these activities need to be monitored to be sure costs are controlled.

After twelve weeks, we might have:

Activity	Budgeted cost	%complete	value completed	actual cost (to date)	cost overrun

A	6000	100	6000	5500	-500

B	4000	100	4000	4100	100

C	16000	100	16000	17000	1000

D	19000	50	9500	8500	-1000

E	20000	75	15000	17000	2000

Total				50500	52300

The cost overrun on C was controlled (but not reduced). The timing on E is good – a week ahead of schedule – but the cost overrun of 2000 needs to be watched closely (?perhaps take some effort out of E, save some costs, allow it to go back to its expected length of time?).  Activity D is behind schedule and is critical – despite the cost savings (which are helpful) it might be in trouble.

Et cetera.