## Klonepalm Basic
Klonepalm Example - basic format
Schedule
| Activity | Node | Predecessors | duration | ES | EF | LS | LF | Slack | Critical?
| Prototype Design | A |  | 90 | 0 | 90 | 0 | 90 | 0 | 1
| Purchase Materials | B | A | 15 | 90 | 105 | 95 | 110 | 5
| Manufacture Prototypes | C | B | 5 | 105 | 110 | 110 | 115 | 5
| Revise Design | D | G | 20 | 129 | 149 | 129 | 149 | 0 | 1
| Initial production | E | D | 21 | 149 | 170 | 173 | 194 | 24
| Staff Training | F | A | 25 | 90 | 115 | 90 | 115 | 0 | 1
| Staff Input on Prototype | G | C,F | 14 | 115 | 129 | 115 | 129 | 0 | 1
| Sales Training | H | D | 28 | 149 | 177 | 166 | 194 | 17
| Proproduction Advertising | I | A | 30 | 90 | 120 | 119 | 149 | 29
| Post-redesign Advertising | J | D,I | 45 | 149 | 194 | 149 | 194 | 0 | 1
| Time = | 194

## PERT
Template for PERT Three-Estimate Approach
|  |  |  | Time Estimates | [8 empty] | On Mean
| Activity | Pred | o | m | p | m | s2 | ES | EF | LS | LF | Slack | Critical Path
| A |  | 76 | 86 | 120 | 90 | 53.7778 | 0 | 90 | 0 | 90 | 0 | Y
| B | A | 12 | 15 | 18 | 15 | 1 | 90 | 105 | 95 | 110 | 5
| C | B | 4 | 5 | 6 | 5 | 0.11111 | 105 | 110 | 110 | 115 | 5
| D | G | 15 | 18 | 33 | 20 | 9 | 129 | 149 | 129 | 149 | 0 | Y
| E | D | 18 | 21 | 24 | 21 | 1 | 149 | 170 | 173 | 194 | 24
| F | A | 16 | 26 | 30 | 25 | 5.4444 | 90 | 115 | 90 | 115 | 0 | Y
| G | C,F | 10 | 13 | 22 | 14 | 4 | 115 | 129 | 115 | 129 | 0 | Y
| H | D | 24 | 28 | 32 | 28 | 1.7778 | 149 | 177 | 166 | 194 | 17
| I | A | 22 | 27 | 50 | 30 | 21.7778 | 90 | 120 | 119 | 149 | 29
| J | D,I | 38 | 43 | 60 | 45 | 13.4444 | 149 | 194 | 149 | 194 | 0 | Y
| Finish | E,H,J | 0 | 0 | 0 | 0 | 0 | 194 | 194 | 194 | 194 | 0 | Y
|  |  | Data |  |  |  |  | Project Duration = | 194
Results
Mean Critical
Path
[5 empty] | m = | 194
[5 empty] | s2 = | 85.6667
[5 empty] | s= | 9.2556
[5 empty] | P(T<=d) = | 0.065192
where
[5 empty] | d = | 180
[5 empty] | If we want P(T<=C) to be | 0.99
[5 empty] | then C= | 215.5318

## Klonepalm PERT
Klonepalm example for PERT
|  |  |  | Time Estimates | [8 empty] | On Mean
| Activity | Pred | o | m | p | m | s2 | ES | EF | LS | LF | Slack | Critical Path
| A |  | 76 | 86 | 120 | 90 | 53.7778 | 0 | 90 | 0 | 90 | 0 | Y
| B | A | 12 | 15 | 18 | 15 | 1 | 90 | 105 | 95 | 110 | 5
| C | B | 4 | 5 | 6 | 5 | 0.11111 | 105 | 110 | 110 | 115 | 5
| D | G | 15 | 18 | 33 | 20 | 9 | 129 | 149 | 129 | 149 | 0 | Y
| E | D | 18 | 21 | 24 | 21 | 1 | 149 | 170 | 173 | 194 | 24
| F | A | 16 | 26 | 30 | 25 | 5.4444 | 90 | 115 | 90 | 115 | 0 | Y
| G | C,F | 10 | 13 | 22 | 14 | 4 | 115 | 129 | 115 | 129 | 0 | Y
| H | D | 24 | 28 | 32 | 28 | 1.7778 | 149 | 177 | 166 | 194 | 17
| I | A | 22 | 27 | 50 | 30 | 21.7778 | 90 | 120 | 119 | 149 | 29
| J | D,I | 38 | 43 | 60 | 45 | 13.4444 | 149 | 194 | 149 | 194 | 0 | Y
| Finish | E,H,J | 0 | 0 | 0 | 0 | 0 | 194 | 194 | 194 | 194 | 0 | Y
|  |  | Data |  |  |  |  | Project Duration = | 194
Results
Mean Critical
Path
|  |  | m = | 194
|  |  | s2 = | 85.6667
|  |  | s= | 9.2556
|  |  | P(T<=d) = | 0.065192
where
|  |  | d = | 180
20
|  |  | If we want P(T<=C) to be | 0.99
|  |  | then C= | 215.5318

## Baja Burrito Crashing
Baja Burrito Project Scheduling Problem with Time-Cost Trade-offs
[7 empty] | Max | Cost per
|  |  | Time |  | Cost |  | Time | week saved | Time
| Activity | Pred | Normal | Crash | Normal | Crash | Saved | (CC-NC)/(NT-CT) | Reduce | ES | EF | LS | LF | Slack | Critical
| A |  | 5 | 3 | 25000 | 36000 | 2 | 5500 | 0 | 0 | 5 | 0 | 5 | 0 | Y
| B | A | 1 | 0.5 | 10000 | 15000 | 0.5 | 10000 | 0 | 5 | 6 | 7 | 8 | 2
| C | A | 3 | 1.5 | 18000 | 22000 | 1.5 | 2666.6667 | 0 | 5 | 8 | 5 | 8 | 0 | Y
| D | A | 2 | 1 | 8000 | 12000 | 1 | 4000 | 0 | 5 | 7 | 17 | 19 | 12
| E | A | 4 | 1.5 | 8000 | 15000 | 2.5 | 2800 | 0 | 5 | 9 | 21 | 25 | 16
| F | B,C | 1 | 0.5 | 12000 | 15000 | 0.5 | 6000 | 0 | 8 | 9 | 8 | 9 | 0 | Y
| G | F | 4 | 2.5 | 20000 | 30000 | 1.5 | 6666.6667 | 0 | 9 | 13 | 9 | 13 | 0 | Y
| H | G | 2 | 1.5 | 12000 | 17000 | 0.5 | 10000 | 0 | 13 | 15 | 15 | 17 | 2
| I | G | 4 | 2.5 | 13000 | 21000 | 1.5 | 5333.3333 | 0 | 13 | 17 | 13 | 17 | 0 | Y
| J | H,I | 2 | 1.5 | 10000 | 16000 | 0.5 | 12000 | 0 | 17 | 19 | 17 | 19 | 0 | Y
| K | I | 2 | 1 | 8000 | 12000 | 1 | 4000 | 0 | 17 | 19 | 20 | 22 | 3
| L | D,J | 3 | 1.5 | 14000 | 22000 | 1.5 | 5333.3333 | 0 | 19 | 22 | 19 | 22 | 0 | Y
| M | K,L | 3 | 1.5 | 10000 | 18000 | 1.5 | 5333.3333 | 0 | 22 | 25 | 22 | 25 | 0 | Y
| N | M | 3 | 1 | 6000 | 9000 | 2 | 1500 | 0 | 25 | 28 | 26 | 29 | 1
| O | E,M | 4 | 2.5 | 8000 | 14000 | 1.5 | 4000 | 0 | 25 | 29 | 25 | 29 | 0 | Y
| P | J | 4 | 2.5 | 18000 | 26000 | 1.5 | 5333.3333 | 0 | 19 | 23 | 25 | 29 | 6
| Finish | [8 empty] | 29 | 29 | 29 | 29
[7 empty] | Finish Time = | 29
[7 empty] | Total Cost = | 200000